Arctic SDI

Secretariat for the Chair of the Arctic SDI Board

Activity Plan until 31 January 2015

- Logistics and practicalities in relation to Board Meeting

Invitation to Board Meeting 15 June 2014

- 20 – 21 November 2014

- Reykjavik, Iceland

- Explaining the procedure preparing the Board Meeting (deadlines, NCP meeting etc)

- Deadline for submission of documents from NCP to Board (31 October 2014)

- Provisional Agenda

Invitation to National Contact Point Meeting 15 June 2014

- 15 – 17 October 2014

- (Ottawa, Canada)

- Explaining the procedure preparing the Board Meeting (deadlines, NCP meeting etc)

- Deadline for submission of documents and items for the provisional agenda – including items for the Board Meeting draft agenda (1 October 2014)

- Provisional Agenda for the Board Meeting

- Provisional Agenda for the NCP Meeting - input from NCP’s and WG Lead Countries

- Briefing note to the Board Members 15 June 2015

- The Annotated Agenda and documents for the Board Meeting to be sent out 5 November 2014

- The Annotated Agenda and documents for National Contact Point Meeting to be sent out 3 October 2014

- Draft Minutes of the meetings to be presented at the end of the meetings and send out for comments within 2 weeks after the Board Meeting and hereafter a finalized version to be sent out after 2 weeks.

- Approval procedure for Protocols

- Arrange necessary actions to hand over the Chair of the Board to USGS

- Joint meetings with the Communication Working Group