## Table of Actions & Decisions
Decisions and Action Items from Nov 2014 Arctic SDI Board Meeting |  | This table is sorted by Activity or Document and can be used to cross reference Decisions and Actions from the 2014 Reykjavik Board Minutes
Decisions and Action Items from Nov 2014 Arctic SDI Board Meeting. | Task | Actions & Decisions | Board Minutes Section | Status/ Notes
ROWS 4-15 HAVE BEEN INCORPORATED INTO THE JUNE 2015 BOARD AGENDA - APPENDIX 1
Board Decisions with No Action:
| Reykjavik Board Meeting Agenda was approved |  | 2
| Secretaries for Board Meeting approved | Eydís L. Finnbogadóttir, Iceland and Lorna Schmid, USA | 2
| 2014-Feb Board Protocols (Minutes) approved |  | 3
2014-Reston-Pending Actions:
| Reston Action Item 7: Russia to resolve legal issues with intention of providing Russian data to the Arctic SDI Web Map Service | Update: Russia stated that there are still some details they are working through with regard to data sharing and they expect everything to be solved in 2015, hopefully in the spring. | 4.g. | Proposed Agenda Item for June 2015 Board Meeting
Pending Actions (June 2015 Board Meeting
| Distribution of Signed MOUs to all Countries | ACTION: Distribution of the Signed MOUs to signatories who were not present: Magnús Guðmundsson, Iceland will mail the copy to Andrey Mukhin, Russia. Lorna Schmid, USA, will mail the copy to Prashant Shunkle, Canada. Kristian Møller, Denmark took the copy for Greenland | 4.a. | MOU for Canada provided to Cameron Wilson, NCP. Magnús Guðmundsson mailed Russian Federation copy to Andrey Mukhin.
| June Board Meeting | DECISION: The Board decided that the next Board Meeting will take place in Copenhagen, Denmark. This meeting will allow the Board to be presented the status and progress on the updated Arctic SDI Strategic Plan and its Strategic Roadmap with prioritized objectives and realistic targets, which the Board has requested. ACTION: Canada and US Board Members need to check their calendars. Magnus will check the dates. First choice is June 4, 2015. Second choice is June 25, 2015 | 8 | Update: The Board has selected June 4 as the date
|  | ACTION: The Board discussed the UN-GGIM meeting in NYC in August and that most Board Members will be there, so perhaps there will be a dinner meeting of the Board Members. | 8 | Included in the agenda for the 4 June Board Meeting. Also requesting Board input on attendance and potential presentation for Calendar of Events.
|  | ACTION: The Secretariat will ensure that the June Board Meeting will cover the topic of what constitutes a quorum for the Board. | 1 | Governance Document Section 4.1.a. updated with proposed text based on Arctic Council procedures.
|  | DECISION: The Board meetings will be held at least once a year. Board and Executive Board Meetings will be held via Skype as necessary between Board Meetings. | 8 | Reflected in Governance Document
|  | ACTION: Board will decide when the proposed 2016 Board Meeting will occur: First choice is June 14-16, 2016 (TBD) | 8
Arctic Council Participation:
| CAFF WG Activities | DECISION: The Board agrees to endorse the current level of technical engagement with CAFF to provide visible services to Arctic Council based on Arctic SDI best practices, and to support continued dialogue on temporal data standards and technology with inclusion of nations' standards representatives as required. | 5.e. | For details of engagement and next steps, see Publishing Assessment of Conservation of Arctic Flora and Fauna data (provided to Board prior to Nov 2014 meeting)
February 2015 Meeting of Strategy WG & WG Leads:
| Strategic Roadmap | DECISION and ACTION: It is suggested to have a meeting of the Strategy Working Group and the Working Group Leads, to be held in February in order to create a strategic roadmap that will: 1) Ensure there is a common understanding of all the work being done across the Working Groups by diagramming the cross-cutting activities and relationships of the Working Groups, 2) Ensure that the strategic roadmap falls within current work and obligations for each country with regard to the MOU and the on-going work of each country, and 3) Identify any gaps or issues with the current Strategic Objectives | 4.a.
| Feb Meeting Preparation | ACTION: The Board requests that the Strategy Working Group, in coordination with the Secretariat, create an annotated Agenda for the meeting to ensure that there are concrete accomplishments, or outputs, from the meeting. This annotated agenda will incorporate the Board Meeting actions and decisions. | 6
Governance Document:
|  | DECISION: Secretariat Responsibilities include the governance Policies, which will be documented in the new Arctic SDI Governance Document. ACTION: The Secretariat will assemble the DRAFT Governance Document, obtain input from the National Contact Points and Working Group Leads, and then submit the document to the Board for approval via email | 5.d. | Sent as part of package of documents to the Board
| Board Meetings without all eight Arctic States present | In the event that a meeting is held without the attendance of all eight Arctic States, the positions of all States present will be documented in the draft minutes which are to be sent to all countries within 14 days. Each Arctic State can provide comments, questions, and/or approval for decisions and actions in writing as part of the approval process for the Board Minutes within 21 days. Allowing time for communication, if necessary, this process will result in final resolution of the motions to be completed within 45 days after receiving the Draft Board minutes. In the absence of comments from a State within the agreed upon timeframe, it will be assumed that that State agrees with the Board minutes and Board decisions and actions. | 1 | Reflected in Governance Document
| Managing Board Minutes | DECISION: The Board, including Canada, approves the method documented above for managing this November 2014 Board Meeting. Further the Board approves this method for future meetings. It was pointed out that the 45-day timeframe should be the maximum time; the process of finalizing meeting minutes should occur as quickly as possible. (See Board Minutes for content) ACTION: The Secretariat will add this decision to the new Governance document [ refers to the decisions and agreed process regarding Board Minutes and Meetings without all 8 Board Members present]. | 1 | Reflected in Governance Document
|  | DECISION: The Board agreed that all documents required for any Board Meeting would be received by the Board 14 days prior to the start of the Board Meeting. The Board may not accept documents received less than 14 days in advance. | 1 | Reflected in Governance Document
| Governance TOR will be incorporated into Governance Document | DECISION: The Board, including Canada, approves the method documented above for managing this November 2014 Board Meeting. Further the Board approves this method for future meetings. It was pointed out that the 45-day timeframe should be the maximum time; the process of finalizing meeting minutes should occur as quickly as possible. (See Board Minutes for content) | 4.b.
|  | DECISION and ACTION: The Secretariat will DRAFT an updated Governance Document which will incorporate the Governance ToR and incorporate the new decisions documented in these minutes. The updated DRAFT will be provided to the Board for approval via email. | 4.b. | Sent as part of package of documents to the Board
| Arctic SDI representation and calendar update process will be documented in Governance Document |  | 4.i.
| Arctic SDI Working Group Participation | ACTION: The Secretariat will include and maintain information on Working Group membership in the new Governance Document. | 5
|  | Russia will provide a new person to join the Strategy Working Group and continue participation in the Technical Working Group. US will participate on the Communications Working Group, Rebecca Anderson will continue to lead the Strategy Working Group and Lorna Schmid will join as the US NCP. The US will continue participation in the Operational Policy Working Group with Ingrid Verstraeten and Lorna Schmid will also join | 5
| Posting Documents on-line | DECISION: All documents requested by the Board, or developed by Working Groups, prior to them being added to the Arctic SDI Public Website, will be in a PDF format that cannot be edited and have a DRAFT Watermark that will only be removed after final acceptance at the appropriate level and after editorial review. ACTION: The Communication Working Group will document the process for posting documents on the Website that will become part of the Arctic SDI Governance Document. | 5.c.
| Membership of Secretariat eventually will follow Executive Board | DECISION: The Secretariat membership will follow the Executive Board. Other countries will continue as supporting countries at least until the Governance, Roadmap and the 5-year Strategy documentation is completed | 5.d. | As of February 2015 US lead, Canada, Finland, Denmark, Norway and Sweden supports
| Communicating with the Board and Document Approval | DECISION: The Board is acknowledging that they will need to be more active if they are to review and approve all documents as described in these minutes. ACTION: Any modifications or changes required to continue the work of any Working Group will be documented and sent forward for approval by the Executive Board, minimally, or the Board. | 5.d.
|  | DECISION: When communicating with the Board via email the Subject must reflect “ACTION REQUIRED – Arctic SDI Board” and the email will provide specific information about when a response is required, usually this will be within 10 days. If there is no response by a Board Member it will signify their acceptance of the action, or decision. | 5.d. | Reflected in Governance Document
|  | DECISION: All Working Group documents subject to Board Meetings and Decisions will be provided to the Secretariat with a cc to the National Contact Points. The Secretariat will forward the documents to the Board for meetings or decisions. | 5.d. | Reflected in Governance Document
|  | DECISION: Technical decisions can be made by the Working Groups as long as they adhere to mandates from the Board and previously agreed on standards from the finalized Roadmap and updated Strategic Plan and Objective Implementation Plans. | 5.d.
|  | DECISION: To ensure a clear understanding of proposed policy changes or requirements which need addressing between Board Meetings, the Board Chair may call a Board Meeting via Internet in order for the Secretariat or Working Groups to provide a briefing. | 5.d.
Document Consolidation:
| Streamline Arctic SDI Documentation | DECISION and ACTION: The Secretariat, Strategy Working Group and the Working Group Leads will streamline the Arctic SDI documentation. | 6
|  | DECISION: The Terms of Reference for the Working Groups will no longer be separate individual documents, but will be incorporated into the Arctic SDI Strategic Plan and the new Roadmap and Arctic SDI Governance Document. As further reflected in the decisions and actions under Agenda Item 6 Arctic SDI Strategy Working Group Discussion, it was decided that if Working Groups have a need to maintain internal ToR to aid in their work the Board does not need to approve or review these documents. ACTION: This will be accomplished by building on the good work already completed so that the new Governance Document, Arctic SDI Roadmap, and the updated Arctic SDI Strategic Plan 2015-2020, and the Objective Implementation Plans will incorporate and replace the Framework Document, Terms of Reference documents and Activity Plans. | 4.c.
|  | DECISION: If Working Groups still need ToR and Activity Plans the Board does not need to see these documents and they should not reside on the public Web site. | 6 | Reflected in Governance Document
Framework Document
| Framework will be modified to serve as a Historic Reference Document | DECISION: The Arctic SDI Framework needs to be modified to serve as a historical reference document. Appendices will need to be evaluated for deletion so as not to conflict with other documents provided by the Arctic SDI. For example, Terms of Reference can be removed as appendices. ACTION: Norway will work with Sweden and the US to make the modifications for final review of the Arctic SDI Framework by the Board in the June meeting | 4.d.
|  | As with the ToR and Activity Plans the Arctic SDI Framework will be incorporated into the Arctic SDI Strategic Plan, Objective Implementation Plans, the new Roadmap and Arctic SDI Governance Document as necessary. | 4.d.
General Purpose Fact Sheet & Slide Show:
|  | DECISION: The Arctic SDI needs to have a general-purpose fact sheet and two “standardized” slide shows that can be used in multiple scenarios to ensure consistent representation of the Arctic SDI. One slide show for general audiences and one for technical audiences; the slide shows may share common slides. | 4.f. | Fact Sheet has not yet been created. Norway discussed having a communications professional work on this.
|  | The slide decks and fact sheet should be evaluated at least every 6 months to determine if updates are necessary. | 4.f. | Reflected in Governance Document
| General Purpose Fact Sheet | ACTION: The Board asks the Communication Working Group to create a fact sheet for the Arctic SDI that can be used in multiple scenarios. A good “model” that was referenced by the Board was the UN-GGIM – Global Geodetic Reference Frame Working Group flyer/newsletter à http://ggim.un.org/docs/meetings/GGIM4/UN%20GGIM_Flyer_april2014.pdf. Draft will be ready for Board Approval at the next Board meeting in June 2015. | 4.f. | Fact Sheet has not yet been created. Norway discussed having a communications professional work on this.
| General Use Slide Show | ACTION: The Board asks the Communication Working Group to draft the “standardized” slide shows on how to present aspects of the Arctic SDI. Slide show development will be prioritized as part of the new Roadmap with draft provided to the Board for approval via email. [Process for Board approval will be updated as per these minutes in the new Arctic SDI Governance Document.] | 4.f. | Technical, Standard and Supplemental Standard slideshow sent as part of package of documents to the Board. Use of presentation slides is meant to be adjusted based on target audience
Arctic SDI Calendar:
|  | DECISION: The Board will approve Arctic SDI representation at all major meetings. | 4.i. | Reflected in Governance Document
|  | DECISION: When possible, the Board Chair should represent the Arctic SDI at higher level meetings, such as the UN-GGIM meeting in USA in August as well as with other higher level meetings / conferences, and Arctic Council Secretarial Meetings | 4.i. | Reflected in Governance Document
| Create approved calendar using new governance process | ACTION: The Secretariat will be notified, with a cc to all National Contact Points, of major meetings or formal presentations regarding the Arctic SDI in order to obtain approval of the Board, or the Executive Board, to include: 1) Meeting name and location, 2) Who is attending and actively participating, and in what context, and 3) Whether a presentation is to be made, or if an invitation should be sought, and the topic or focus of that presentation | 4.i. | Reflected in Governance Document
|  | ACTION: The new governance procedure documented in these minutes under the Agenda Item 5.d. for using the Secretariat to obtain Board approval between meetings will be put into place immediately to adopt an agreed upon Calendar of Events for the Arctic SDI. (The Secretariat will email the updated Calendar to the Board before the proposed February Strategy Working Group and Working Group Leads meeting documented under Agenda Item 6.) | 4.i. | Sent as part of package of documents to the Board
|  | ACTION: Once meeting attendance is approved the Secretariat will notify the Communications Working Group so that the Web site Calendar can be updated. | 4.i. | Reflected in Governance Document
General Strategic Plan, Roadmap and Objective Implementation Plan Decisions
|  | DECISIONS: The Board made the following decisions regarding the Arctic SDI Strategic Plan, Objective Implementation Plans and Roadmap:* | 6 | *The bulleted list associated with this decision has been incorporated into this table.
Arctic SDI Strategic Plan 2015-2020:
| General Decisions by Board | DECISION: In order to facilitate the development of the new Arctic SDI Roadmap, Governance Document and updated Arctic SDI Strategic Plan and Objective Implementation Plans the Board accepts the documented modification to the objectives contained below [herein]. | 6 | Actions and decisions are detailed under Objective Grouping
|  | ACTION: The Strategy Working Group will modify the Arctic SDI Strategic Plan with prioritized objectives and realistic targets to be reviewed and approved by the Board. | 6
DECISION: The Strategic Plan should be shorter and more concise than the draft plan submitted to the Board Meeting.
DECISION: Remember that the main objective was to be a good counterpart for the Arctic Council. Therefore, we need to focus on them as the stakeholder to ensure a tight scope.
|  | ACTION: Function of the Secretariat: When the documents are updated they must be checked against the MOU to make sure it is in line. | 6
Arctic SDI Roadmap:
| General Roadmap Decisions or Actions | DECISION: The Board requests that an Arctic SDI Roadmap is created to get an overview of the actions, deliverables and dates associated with the Arctic SDI Strategic Plan 2015-2020. | 6
|  | DECISION: A meeting of the Strategy Working Group and the Working Group Leads is to be held in February in order to create a strategic roadmap ACTION: Roadmap will: 1) Ensure there is a common understanding of all the work being done across the Working Groups by diagramming the cross-cutting activities and relationships of the Working Groups, 2) Ensure that the strategic roadmap falls within current work and obligations for each country with regard to the MOU and the on-going work of each country, and 3) Identify any gaps or issues with the current Strategic Objectives | 6 | Also captured in Minutes section 4. Under "Winter Meeting" Grouping
|  | DECISION: Roadmap needs to be clear and concise | 6
|  | DECISION: Short term and long term activities (timelines) deliverables need to be defined | 6
Glossary of Terms:
|  | Decision: There will be a Glossary of Terms for the Document to ensure that everyone has a common understanding. | 6 | Proposed Agenda Item for June 2015 Board Meeting. Request Board input on Responsible Working Group.
|  | ACTION: The Strategy Working Group and the Working Group Leads will draft definitions for reference and thematic data to be adopted by the Arctic SDI that are in alignment with the MOU and meet the needs and requirements of its users and data providers. This definition will be forwarded to the Board for approval before its adoption using the new governance process documented in these minutes. | 6. objective 2 | See Memo Request for Approval of Definitions for Reference and Thematic Data
Strategic Objective Implementation Plans:
| General Objective Implementation Plans Decisions or Actions | DECISION: There should be 3, or less, Key Performance Indicators for each Objective | 6
| Objective 1 - Address Needs of Arctic Council and Other Users: | DECISION: The Priorities will be set under Objective 1 by the Strategy Working Group | 6
|  | DECISION: The Strategy Group will lead Objective 1. The work will be supported by Communications and other Working Groups. | 6
|  | ACTION: The Strategy Working Group will evaluate available Reference Data and Thematic Data for incorporation into the Arctic SDI as part of the activities to gather and analyze information from users on their needs. | 6. objective 1.
|  | DECISION: The data that will be incorporated into the Arctic SDI will be determined as part of Objective 1. [The actions to incorporate the data are the functions of Objective 2 & 3.] | 6. objective 1. | [copied to Objective 2 & 3]
|  | DECISION: Geographic reference datasets to be considered for inclusion are those which are owned, or managed, by the NMAs. | 6. objective 1. | See Memo Request for Approval of Definitions for Reference and Thematic Data
| Objective 2 - Provide reference datasets from Arctic Council nations: | ACTION: Paragraph 2 in the Background may need to be moved to the Objective 3 if it would be required based on the definition of thematic data. Consideration of the Boards position that data, which is to be incorporated into the SDI, is data identified by users as being important AND data which is supported by users who want to contribute to the SDI or by the NMAs as appropriate. | 6. objective 2
|  | DECISION: The actions to incorporate the data are the functions of Objective 2 & 3 | 6. objective 2
|  | DECISION: Objective 2 and 3 will implement what is identified by the work of Objective 1. | 6
| Objective 3 - Facilitate access to thematic data sets: | DECISION: Looking at Objective 3 under Strategic Approach section, the Strategy Working Group will be responsible to identify the primary users under Objective 1. As previously stated, priorities will be set under Objective 1 and Objective 2 & 3 will implement what is identified by the work of Objective 1. | 6. objective 3
DECISION: The actions to incorporate the data are the functions of Objective 2 & 3
|  | DECISION: Objective 2 and 3 will implement what is identified by the work of Objective 1. | 6
| Objective 4 - Data is Interoperable: | No major comments by the Board. | 6. objective 4
| Objective 5 - Provide an operational policy framework for the Arctic SDI: | No major comments by the Board. | 6. objective 5
| Objective 6 - Communications: | DECISION: Change the name of this Objective to Communications | 6. objective 6
| Objective 7 - Resources and Financing: | DECISION: Remove Objective 7 from the Strategic Plan Implementation Plan. However, the Roadmap, Strategic Plan and Objective Implementation Plans must state that the Strategies used to implement the Arctic SDI will be accomplished under the terms of the MOU and there must be a specific review to ensure that it complies. | 6. objective 7