Web Map implement phases

Phases for technical implementation

- Summary in table, details under table -

In this document the phases for the technical implementation are described, activities within the different phases and required board decisions, a precondition for the TWG to finalize the phases:

- The table is a summary of the information further down on pages 3 ff.

- Work load estimation is indications - some of them concern all participating organisations.

- Please note that the activities involve much more than WMS-services.

Rough total workload estimation according to below:

- 2014 - 2 man years/distributed among participating organizations - phases 1 - 4

- 2015 - depending on level of ambition - phase 5

Days = less than 7; Weeks = less than 4;

| PHASE | DATE | ACTIVITY | DECISIONS NEEDED TO FULFIL PHASE | WORK LOAD FOR TWG - ROUGH ESTIMATION |
| --- | --- | --- | --- | --- |
| 1 | Feb, 2014 | View services |  |  |
|  |  | Download services |  |  |
| 2 | Mar 2014 |  | Decision on which Cloud Service to be used |  |
|  |  |  | Decision on Lead Country for central server |  |
|  |  |  | Permission to launch WMS services publicly |  |
|  |  |  | Permission to store images of the data from each country on a server in the cloud |  |
|  |  | Operational platform-administrative |  | Week |
|  |  | Data streams |  | Days |
|  |  | Cartographic specification |  | Weeks |
|  |  | View services - start |  | Days/country |
| 3 | Aug 2014 |  | Move the web portal to cloud server or keep it where it is? |  |
|  |  | Operational platform-installations |  | Weeks |
|  |  | Cartographic specification |  | Days |
|  |  | View services - continued |  | Weeks+days/country |
|  |  | Metadata catalogue |  | Days |
|  |  | Download services – start - unclear task |  | Weeks-Months? |
|  |  | Arctic SDI Web Portal |  | Week |
|  |  | Test Operational Environment |  | Week |
| 4 | Nov 2014 | Download services – continued- unclear task |  | Weeks |
|  |  | Metadata catalogue |  | Weeks+days/country |
|  |  | Test on Users |  | Days |
| 5 | End 2015 |  | Shall we go for download services on reference data in the Arctic? |  |
|  |  |  | Is it enough with the links to existing download services in the metadata catalogue? |  |
|  |  | Increase knowledge and use |  |  |
|  |  | Metadata catalogue - continued |  |  |
|  |  | Download services - continued |  |  |

For more details, refer to below.

Phases for technical implementation

In this document we describe the phases for the technical implementation and what is within the phases and finally what board decisions are required for the TWG to finalize the phases.

Rough workload estimation according to below:

2014 - 2 man years/distributed among participating organizations - phases 1 - 4

2015 - depending on level of ambition - phase 5

# Phase 1)

Deadline: February 13, 2014

## View services

- Finalize the 1:1M data and connect it with the cascading service

- Create a first Map Cache for the cascaded background map

- Fix the example OpenLayers web viewer so it works for demo

## Download services

- Initiate cooperation with CAFF regarding the Data delivery mechanism project.

# Phase 2)

Deadline: SAO meeting (March 25-27, 2014)

## Required decisions:

- Need a decision on which Cloud Service to be used

- Need a decision on Lead Country för central server

- Need permission to launch the WMS services publicly

- Need permission to store images of the data from each country on a server in the cloud

## Operational platform (week)

- The needed administrative activities are finalizes based on decided platform

- Platform established and permissions are distributed

## Data streams (days)

- Link to an example of streamed data, e.g. from a weather station or water level gauge -

## Cartographic specification (weeks)

- Adjustment to mirror the ELF specification

- Adjustments to fulfil requirements from Russia

## View services (days/country)

- Adjustments to national WMS are done

- Adjustments to cascaded service is done

# Phase 3)

Deadline: Summer, 2014

## Operational platform (weeks)

- Installation of web server

- Installation of application server

- Installation of Content Management System (Arctic SDI web portal) - If decided

- Installation of GeoPortal

- Installation of tools for Central Services (Cascading Service, Map cache)

## Cartographic specification (days)

- Adjustment to mirror the ELF specification

- Adjustments to fulfil requirements from Russia

## View services (weeks + days/country)

- If needed, adjustments to national WMS are done

- If needed, adjustments to cascaded service is done

- Move Cascaded service from temporary environment to operational

- Add the Russian WMS to the cascaded service

- Create a complete Map Cache

## Metadata catalogue (days)

●	Metadata for the Arctic SDI National WMSs’ are created 1/country

## Download services (weeks-month)? - unclear task

- Proof of concept is done for the Data delivery mechanism project with CAFF.

- Demo example is created for the Data delivery mechanism project.

## Arctic SDI Web Portal (week)

- Move web portal to operational platform?

## Test Operational Environment (week)

- Test access to server for all permitted technicians

- Test access to web pages?

- Test access to cascaded service

- Test access to the Map cache

- Test access to GeoPortal and catalogue service

- Test the Map cache - is it acceptable for the users?

## Required decisions:

- Shall we move the web portal to the cloud server or keep it where it is?

# Phase 4)

Deadline: November, 2014

## Download services (weeks) unclear task

- A prototype Data delivery mechanism is available for CAFF.

## Metadata catalogue (weeks + days/country)

- Metadata keywords decided

- Metadata for the Arctic SDI National WMSs’ are created

- The work is started with implementation of Arctic SDI keywords in national metadata

## Test on Users (days)

- Test the operational central services on the users (CAFF and others)

-----------------------------------------------------------------------------------------------------------------------

## Phase 5)

Deadline: End 2015

## Increase knowledge and use

- Use cases for several Arctic council  WGs in place

## Metadata catalogue

- Work with specific entities e.g. CAFF

- Harvesting of Metadata from National SDI’s to the Arctic SDI catalogue has started

## Download services

- Discussions on how to implement download services on reference data has started?

- Implementation of download services for reference data?

## Required decisions:

- Shall we go for download services on reference data in the Arctic?

- Is it enough with the links to existing download services in the metadata catalogue?